## Sheet1
|  |  | Neaz Mahmud |  | Moshiour Rahman Prince |  | Abdullah Al Forkan |  | Eze Nnaemeka Valentine
Serial | Task | Short summary | Todo | Done/Not Done | Todo | Done/Not Done | Todo | Done/Not Done | Todo | Done/Not Done
1 | SysML Diagrams |  | Parametric Constraints Diagram | ✔️ | Requirement Diagram | ✔️ | Block Diagram | ✔️ | Allocation Diagram | ❌
|  |  | Sequence Diagram | ✔️ | State Machine Diagram | ✔️ | Activity Diagram | ✔️ | Package Diagram | ✔️
2 | 1st Prototype |  | Sequence Diagram Update | ✔️ | Requirement Diagram Update | ❌ (due to sickness) | Block Diagram Update | ✔️ | Allocation Diagram | ❌
|  |  | Code | ✔️ | State Machine Diagram Update | ❌ (due to sickness) | Activity Diagram Update | ✔️ | Package Diagram Update | ✔️
|  |  | Presentation Preparation | ✔️ (50%) |  |  | Presentation Preparation | ✔️ (50%) | Block Diagram | ✔️
|  |  | Implementation | ✔️ |  |  | Simulation | ✔️
3 | CAD Design |  | Assembly | ✔️ | Arduino Holder | ✔️ | Color Sensor Holder | ✔️ | Didn't do the task he was assigned to | ❌
|  |  | Ultrasonic sensor Holder | ✔️ | Motor Driver | ✔️ | Motor Holder | ✔️
|  |  | IR sensor Holder | ✔️ | Base Design | ✔️ | Battery Holder | ✔️
|  |  | Overall Design Idea | ✔️ | Front Wheel | ✔️
|  |  | Top Part | ✔️
4 | SysML Diagrams |  | State Machine Diagram Final | ✔️ | Requirement Diagram Final | ✔️ | Block defination diagram | ✔️
|  |  | Sequence Diagram Final | ✔️ |  |  | Internal Block Diagram | ✔️
|  |  | Flowchart | ✔️
5 | Programming |  | Line Following | ✔️ | Color Sensor Algorithm | ✔️ | Ultrasonic Sensor Algorithm | ✔️
|  |  | Turning at specific Point | ✔️
|  |  | Junction Count | ✔️